## List1
2,8		Financial plan					Cost specification
Duration		Version	Activity title	Activity scope (ČM)	DIRECT COSTS (in EUR)				INDIRECT COSTS (v EUR)	TOTAL					Version	Activity title	Cost specification
				2000	work	service	investments	travel expenses					service	investments	travel expenses
6	0,0208955224	A 1.1	Project specification	0,13	260		2050	100	52	2462	new headphones for voice chat	trip to Maribor for 2 to present the idea					A 1.1	Project specification		50 – new headphones for voice chat	100 - trip to Maribor for 2 to present the idea
5	0,0208955224	A 2.1	Project managment-risk managment	0,1	200				40	240					500 – new software
5	0,0208955224	A 3.1	Traning in information design	0,1	200		50		40	290					1500 – new hardware device
5	0,0208955224	A 4.1	Information design	0,1	200				40	240	training for one persn					A 3.1	Traning in information design		training for one persn
5	0,0208955224	A 5.1	Tutorial development	0,1	200		70		40	310	camera loan					A 5.1	Tutorial development		camera loan
8	0,0208955224	A 6.1	Front-end design	0,17	340				68	408					A 16.1	Documentation		paper
10	0,0208955224	A 7.1	Front-end deployment	0,21	420				84	504					A 17.1	Prepare presentation			trip to Maribor for 2 to present the solution
5	0,0208955224	A 8.1	Testing, error handling and reparing	0,1	200				40	240
10	0,0208955224	A 9.1	Development of game logic	0,21	420				84	504
14	0,0208955224	A 10.1	Deployment of game logic	0,29	580				116	696
8	0,0208955224	A 11.1	Testing of running code, error handling and reparing	0,17	340				68	408
16	0,0208955224	A 12.1	Back-end coding	0,33	660				132	792
10	0,0208955224	A 13.1	Testing FCFS, fails handling and reparing	0,21	420				84	504
12	0,0208955224	A 14.1	Integration (Back-end, front-end, logic)	0,25	500				100	600
5	0,0208955224	A 15.1	Testing integrated system	0,1	200				40	240
5	0,0208955224	A 16.1	Documentation	0,1	200		10		40	250	paper
5	0,0208955224	A 17.1	Prepare presentation	0,13	260			100	52	412	trip to Maribor for 2 to present the solution
134		0	0	2,8	5600	0	2180	200	1120	9100

:	21.5 working days – 5.94h/day = 360h
2,8
Duration	sum(PM)/total

7	0,0207407407
6	0,0207407407
5	0,0207407407
5	0,0207407407
10	0,0207407407
16	0,0207407407
5	0,0207407407
8	0,0207407407
10	0,0207407407
10	0,0207407407
10	0,0207407407
5	0,0207407407
4	0,0207407407
10	0,0207407407
5	0,0207407407
5	0,0207407407
10	0,0207407407
4	0,0207407407
4	0,0207407407
135