## dependencies
ID | Task name | Duration (in days) | Dependencies
A1 | Product specification | 6
A2 | Project managment-risk managment | 5
A3 | Traning in information design | 5 | A1 A2
A4 | Information design | 5 | A3
A5 | Tutorial development | 5 | A1 A2
A6 | Front-end design | 8 | A4,A5
A7 | Front-end deployment | 10 | A6
A8 | Testing, error handling and repairing of the front end | 5 | A7
A9 | Development of game logic 1v1 | 10 | A1 A2
A10 | Deployment of game logic 1v1 into javacsript code | 14 | A6
A11 | Testing of running code representing the game logic, fails handling and repairing | 8 | A10
A12 | Back-end coding | 16 | A1 A2
A13 | Testing FCFS, Fails handling and repairing | 10 | A12
A14 | Integration (Back-end, front-end, application logic) | 12 | A8,A11,A13
A15 | Testing integrated system,fails handling and reparing | 5 | A14
A16 | Documentation | 5 | A15
A17 | Prepare presentation | 5 | A15