## List1
2,8		Financial plan
Duration		Version	Activity title	Activity scope (ČM)	DIRECT COSTS (in EUR)				INDIRECT COSTS (v EUR)	TOTAL
				2000	work	service	investments	travel expenses
7	0,024137931	A 1.1	Project proposal and specification	0,17	340					340
6	0,024137931	A 2.1	Project managment-risk managment	0,14	280					280
5	0,024137931	A 3.1	Traning in information design	0,12	240					240
5	0,024137931	A 5.1	Tutorial development	0,12	240					240
10	0,024137931	A 9.1	Developement of game logic	0,24	480					480
16	0,024137931	A 12.1	Back-end coding	0,39	780					780
5	0,024137931	A 4.1	Information design	0,12	240					240
8	0,024137931	A 6.2	Front-end design	0,19	380					380
10	0,024137931	A 13.1	Back-end testing and error handling	0,24	480					480
10	0,024137931	A 7.1	Front-end deployment	0,24	480					480
1	0,024137931	A 10.1	Deployment of game logic 1v1 into javacsript code	0,02	40					40
5	0,024137931	A 8.1	Front-end testing and error handling	0,12	240					240
8	0,024137931	A 11.1	Game logic deployment testing and error handling	0,19	380					380
10	0,024137931	A17.1 A14.1	Integration	0,24	480					480
5	0,024137931	A18.1 A15.1	Integration testing and error handling	0,12	240					240
5	0,024137931	A19.1 A16.1	Documentation and final presentation	0,12	240					240
116				2,78	5560	0	0	0	0	5560

:	21.5 working days – 5.94h/day = 360h
2,8		Financial plan
Duration	sum(PM)/total	Version	Activity title	Activity scope (ČM)	DIRECT COSTS (in EUR)				INDIRECT COSTS (v EUR)	TOTAL
				2000	work	service	investments	travel expenses
7	0,0207407407	A 1.1	Project proposal and specification	0,15	300					300
6	0,0207407407	A 2.1	Project managment-risk management = 33.5h -each day 0.5	0,12	240					240
5	0,0207407407	A 3.1	Traning in information design	0,1	200					200
5	0,0207407407	A 5.1	Tutorial development	0,1	200					200
10	0,0207407407	A 9.1	Developement of game logic	0,21	420					420
16	0,0207407407	A 12.1	Back-end coding	0,33	660					660
5	0,0207407407	A 4.1	Information design	0,1	200					200
8	0,0207407407	A 6.2	Front-end design	0,17	340					340
10	0,0207407407	A 13.1	Back-end testing and error handling	0,21	420					420
10	0,0207407407	A 7.1	Front-end deployment	0,21	420					420
10	0,0207407407	A 10.1	Deployment of game logic 1v1 into javacsript code	0,21	420					420
5	0,0207407407	A 8.1	Front-end testing and error handling	0,1	200					200
4	0,0207407407	A 11.1	Game logic deployment testing and error handling	0,08	160					160
10	0,0207407407	A17.1 A14.1	Integration	0,21	420					420
5	0,0207407407	A18.1 A15.1	Integration testing and error handling	0,1	200					200
5	0,0207407407	A19.1 A16.1	Documentation and final presentation	0,1	200					200
10	0,0207407407	A14.1	Ai development	0,21	420					420
4	0,0207407407	A15.1	Ai deployment and insertion in 11.	0,08	160					160
4	0,0207407407	A16.1	AI testing and error handling	0,08	160					160
135				2,87	5740	0	0	0	0	5740