Requirements: investment

Divide the cost of the project direct costs (labor, services, investment in hardware or software, operators) and indirect costs (the latter may also be a flat, eg. A flat-rate indirect costs amount to 20% of labor costs).
Provide costs for each activity separately. Use the table below.
# All direct costs in the table above, excluding labor costs, specifically rationale (eg. € 50 for registration of internet domain, € 1,500 for the purchase of a computer for development, € 100 for a visit to Maribor conference for two people, and the like).
		List of project products / Release date / 4.11.2016 / 9.11.2016 / 12.11.2016 / 14.11.2016 / 17.11.2016 / 15.12.2016 / 1.12.2016 / 1.12.2016 / 1.12.2016 / 17.12.2016 / 1.1.2017 / NAN / 11.1.2017 / 11.1.2017
Product code	Name of the product		Start date	Release date	Product type
PC 1.1	Requirements specification		2.11.	4.11.2016	PO
PC 1.2	Project proposal		3.11.	9.11.2016	PO
PC 1.3	Project proposal presentation			12.11.2016	PO
PC 5.1	Tutorial description and specification / = what it will / be and what it will include. 13.11			14.11.2016	PO
PC 6.1	Wireframes and sitemaps			17.11.2016	PO
PC 8.1	Frond-end			15.12.2016	DP
PC 11.1	Running code representing the game logic			1.12.2016	DP
PC 13.1	FIFS machmaking system			1.12.2016	DP
PC 14.1	AI Algorithm			1.12.2016	DP
PC 16.1	Artificial inteligence player			17.12.2016	DP
PC 18.1	Final Application			1.1.2017	DP
PC 19.1	Intermediate presentation			NAN	PO
PC 19.2	Documentation			11.1.2017	PO
PC 19.3	Final presentation			11.1.2017	PO

			Financial plan
Start	Finish(isključivo / )	DUration	Version	Activity title	Activity scope (ČM)	DIRECT COSTS (in EUR)				INDIRECT COSTS (v EUR)	TOTAL
						work	service	investments	travel expenses
2.11.	9.11.	7	A 1.1	Project proposal and specification
2.11	Project dedline		A 2.1	Project managment-risk managment
9.11.	14.11.	5	A 3.1	Traning in information design	A1, not A2
9.11	14.11	5	A 5.1	Tutorial development	A1
9.11	19.11	10	A 9.1	Developement of game logic	A1
9.11	25.11	16	A 12.1	Back-end coding	A1
14.11	19.11	5	A 4.1	Information design	A 3
19.11	27.11	8	A 6.2	Front-end design	A4,A5
25.11	5.12.	10	A 13.1	Back-end testing and error handling	A12
27.11	7.12	10	A 7.1	Front-end deployment	A6
27.11 / 27.11	11.12 / 7.12	14 / 10	A 10.1	Deployment of game logic 1v1 into javacsript code	A9
7.11	12.12	5	A 8.1	Front-end testing and error handling	A7
11.12 / 7.12	19.12 / 11.12	8 4	A 11.1	Game logic deployment testing and error handling	A10
19.12	29.12	10	A17.1 A14.1	Integration	All A15 A13 A11 A8
29.12	3.1.2017	5	A18.1 A15.1	Integration testing and error handling	A17 A14
3.1	8.1	5	A19.1 A16.1	Documentation and final presentation	A18 A15
1.12	11.12	10	A14.1	Ai development	A1
11.12	15.12	4	A15.1	Ai deployment and insertion in 11.	A11 A13
15.12	19.12	4	A16.1	AI testing and error handling	A15